## Slide 1: IGT173 – Gateway Delivery of RPC Data
Testing Approach Overview
Post - August Workgroup Update

## Slide 2: Background
Modification IGT173 aims to update the mechanism of delivery of the RPC files from email/portal to IX delivery.
IGT173 has been approved by the IGT UNC Panel, and XRN 5720 has been approved by the DSC Committee. Both changes are targeting the Nov 2024 release for implementation.
To support delivery, a testing window for volunteering parties is being created ahead of delivery.
Only a small number of parties have expressed interest in testing as part of the modification responses.
Pre implementation testing is not planned for all IGT modifications; the approach for IGT173 will be bespoke. As part of IGT173 approval, the testing approach will require panel review ahead of commencement of the testing window.

## Slide 3: Workgroup considerations / recommendations – *Updated*
Confirmation of testing window duration – suggestion 3 weeks (may conclude quicker).
  Window to be just under three weeks – 2 weeks testing and the remaining as contingency. Aug workgroup supported this approach.
Confirmation of testing window commencement date – suggestion 7th – 25th October.
  Xoserve are aiming for the earlier window of 1st -18th Oct (to allow IGTs to simulate live running). Aug workgroup supported this approach.
Workgroup recommendation that the testing scenarios deliver confidence for the approved business rules.
  Do any additional scenario tests need including for any of the business rules?
  Aug 24 workgroup supported including testing for the 5pm on the 5th business day cut off.
Do parties want to test anything which is outside of the stated business rules?
  An example of this is a file which is an inconsistent file size e.g. 10 x larger than normal.
  An IGT supported testing for abnormal file sizes but as not part of the business rules was agreed to be individually added to test log where parties want to check it.
Confirmation of testing parties – so far 2 x IGT and 2 x Shipper volunteers, anyone else?
  Updated to 3 x IGT volunteers at July meeting, no additional volunteers have come forward – Testing leads to be provided to E.ON. No additional volunteers, comms agreed to be issued to ensure awareness of the change as well as a final call for shipper volunteers. Aug workgroup supportive of this approach.
Do volunteering parties want to test with all participants or use a buddy system?
  To replicate live, all participating IGTs will issue to all participating Shippers. Aug workgroup supported this approach.
Do volunteering parties want to have daily check in calls or another frequency?
  Suggestion to hold a mid-morning (11am) call. There will be a minimum of a commencement call on the 1st , a weekly wrap up on the 4th, a 2nd week kick off call on the 7th and a weekly wrap up (and decision on contingency need) on the 11th. All other days will be decided by testing participants who will stand up/down call around needs. Aug workgroup supported this and supported stepping down meetings where they are not required to focus on testing.
How do workgroup and volunteering parties want to capture testing evidence?
  Suggestion to use the testing log template (presented in July). All completed logs to be sent to E.ON at the end of testing to collate to a single log to share with Panel. Aug workgroup supportive of this.
How do workgroup and volunteering parties want to recommend release implementation to Panel?
  Suggestion for the final testing daily call to capture a formal recommendation (similar to a Go/No-Go recommendation) which is then submitted to panel with the test log. Aug workgroup supportive of this approach and also suggested a status updates goes to the Oct workgroup, meeting placeholder to be added (verbal update)

## Slide 4: Workgroup considerations / recommendations – Continued
Testing data to be dummy rather than live
  July workgroup supported using test data and agreed to add it as a note to the scenario tests (next slide). Aug workgroup discussed this and there were different views on content data of the file . The workgroup supported the use of compliant data from the IGTs, as the content is not validated as part of this mod and there is no business rule to mandate population of data. Individual IGTs are to determine content population.
Retention of test data
  As the test data is ‘dummy data’, it has been suggested to delete the data once testing as concluded. This is likely to be parties' data retention policies (and a sensible ask) – to be discuss at the Aug meeting. Aug workgroup agreed this is sensible but the mod does not mandate the approach to be taken so it is down to parties to follow their individual data retention processes.
CDSP attendance for testing
  The CDSP will have representative (Nov 24 Project Manager) for the initial kick-off call, any additional attendance will be by request. Aug workgroup were supportive of this approach
Issue raising to the CDSP
  This will be via uklinkdelivery@xoserve.com and any correspondence sent to include XRN/Mod info in the title as well as cc the Nov 24 Project Manager. All issues submitted to this mailbox are to be captured in the testing log. Aug workgroup supportive of this
Industry Comms ahead of testing
  It has been suggested to issue comms (via the IGT UNC and CDSP) to confirm the testing approach in a bespoke comms and also do a final call for volunteers – to be discussed at the Aug meeting. Aug workgroup supported comms being issued by the IGT UNC and suggested also issuing via JO distribution list too.

## Slide 5: Initial High-Level Testing Scenarios
The IGTs can successfully create a file using the guidance documentation.
Files are successfully cascaded between the IGT / CDSP / Shipper with successful notifications issued.
Files with invalid file extensions fail as expected and unsuccessful notifications are issued.
Files with invalid naming conventions fail as expected and unsuccessful notifications are issued.
Files with incorrect file numberings e.g. TKAB1234 fail and unsuccessful notifications are issued.
Files are issued by the 5pm on the 5th business day cut off
NOTES:
File naming for testing use ‘TN’ rather than production ‘PN’ naming. Should PN files be used this may result in files be loaded into parties live environments.
RPC file data to be compliantly formatted and populated but does not have to replicate live data, can be dummy data.

## Slide 6: Business Rules Testing
Business Rule | Scenario Test | Comment
1 | 1 & 2 | IGT only test for creating the file to send
2 | 2 | IGT, Shipper and CDSP test confirming successful IX delivery
3 | 2 | Delivered via scenario 2, no additional scenarios outlined for this
4 | - | IGTs may want to add in scenarios to test, no current scenarios captured
5 | 1, 2 & 3 | IGT, Shipper and CDSP tests for valid and invalid scenarios
6 | 2 & 4 | IGT, Shipper and CDSP tests for valid and invalid scenarios
7 | 6 | No scenarios currently outlined as timing of the test window does not reflect live Testing to confirm files issued / received by the cut off
8 | - | Avoidance of date statement, no scenarios outlined for this
9 | - | Offline process, no scenarios outlined for this
10 | 2 | Delivered via scenario 2, no additional scenarios outlined for this
11 | 2 | Delivered via scenario 2, no additional scenarios outlined for this
12 | - | No scenarios as this rule is around completing testing
13 | - | No scenarios as this is relates to the post implementation review

## Slide 7: Thank you