## Known Issues - Open
Last Reviewed: 7th November 2024
Iss Ref # | Issue | Details | Date Raised | Raised By | Meeting Reference | Action Required | Last Update | Comments
1 | Cross code modifications | The IGT UNC now points over to various parts of the UNC text and changes to the UNC can affect the alignment of the texts and the integrity of the cross-referencing. Fast track modifications have been raised when these implications have been identified in order to bring both codes back in line | 2017-08-01 | Code Administrator | Modification Workstream 17-08 | Ongoing monitoring of the cross code modifications is carried out via the cross-code tracker (standing agenda item). | 2021-04-07 | Suggest closure as the action taken was to use the Cross Code Tracker, which has been used consistently for some time.
3 | Metering arrangements within the IGT UNC | The uncertainty around the Metering arrangements within the IGT UNC in anticipation that this will be an issue in the future | 2020-04-09 | E.ON | Modification Workstream 20-04 | Establish and outline metering arrangements should the risk arise in the future. See outcomes of the REC and RCC SCR. Metering arrangements for the IGT UNC in the REC have now been published providing certainty this will not be an issue in the future. The Workgroup believed that this risk is still relevant as at March 2024 | 2024-03-14 | This might merge into whatever comes from Code Reform so agreed to keep on - 14/03/24.
4 | MAM /MEM consistency | The following defined terms are used within the IGT UNC: - Meter Asset Manager (MAM) - Meter Equipment Manager (MEM) Both terms make reference to the same role but are used interchangeably within the IGT UNC. The UNC Currently uses MAM and the REC uses MEM. BUUK have suggested that the use of terms be analysed and consideration be given to aligning with MEM (as used in the REC). | 2021-12-21 | BUUK | - | IGT UNC, UNC and REC have been reviewed with regards to the use of terms: - In the IGT UNC, “Meter Asset Manager” is used once, “MAM” is used twice, and “Meter Equipment Manager” is used three times. - The UNC currently use MAM, rather than MEM, and the UNC definition is aligned exactly to the IGT UNC definition. - The REC uses MEM but in their definition they make reference to MAM as follows: "means, as applicable, either: (a) for electricity, the 'Meter Operator Agent' (as defined in the BSC) Appointed by an Electricity Supplier; or (b) for gas, the 'Meter Asset Manager' (as defined in the UNC) Appointed by the Gas Supplier." | 2022-04-14 | March 2022: The Code Administrator recommend alignment to the use of MAM rather than MEM, should alignment be deemed to be required. Reason for this was primarily because IGT UNC has greater ties and dependency to the UNC than we do to the REC. Further, the REC definition of MEM refers directly to MAM, as this is the term used in the UNC and gas generally. When discussed with REC they saw no issue with aligning to MAM over MEM for the same reasons. April 2022:The above update was provided to the Workgroup at their March meeting where it was agreed that those in attendance would think about their preference with regards to MAM/MEM and report back at the April 2022 meeting. The Workgroup agreed that no change to the IGT UNC should be made at this time but that this item should be left on the Known Issues log to ensure a record is kept in case a change is needed in future
5 | Difficulty finding IGT UNC Parties to raise required IGT UNC Modifications. | During 2022 there were multiple Urgent Modification Proposals raised under the UNC that required equivalate Modifications under the IGT UNC. The Code Administrator made multiple attempts to find a sponsor for required Modifications where nessessary. As a result of there not being a sponsor when required the nessessary IGT UNC Modifications were either raised later than ideal. | 2023-01-05 | Code Administrator | 2023-01-12 | To be confirmed | 2023-01-05 | BUUK have come forward to sponsor any required DSR related Modification.
6 | IGT UNC and UNC Cross Code working | At the March 2023 Workgroup meeting some concerns were raised by members that more needed to be done with regards to assessing IGT and IGT UNC impacts from UNC Modifications. | 2023-03-09 | Workgroup | 2023-03-09 | CA to add issue to Known issues register and add item on agenda for April 2023 Workgroup meeting. CA to also ensure a representitive from the CDSP and the Joint Office are in attendence. | 2023-04-03
7 | IGT UNC Panel Quoracy | As of the August 2024 Panel meeting the IGT UNC Panel will be non-quorate. | 2024-07-11 | Workgroup | 2024-07-11 | CA to issue regular industry notices regarding vacant Shipper seats in an effort to fill. CA to put in place previous processes to ensure Panel business can continue until the Panel is quorate again. | 2024-07-11

## Housekeeping - Open
Last Reviewed: 7th November 2024
Date Raised | Raised By | Section of Code | Legal Text | Reason for change | Modification addressing the change | Targeted Implementation Date | Notes
2021-05-13 | Energy Assets | Ancillary Document - CSEP NExA Table | TBC | This ancillary document refers to 'Pipeline Operation Agency', which is a defined term in the IGT UNC and this refers to section N1.1. However, what is defined there is the CDSP, so the reference is not accurate. | TBC | TBC | Reference to Pipeline Operation Agency noted under "Reason for Change" not within the CSEP NExA Table docment. Recommend closing.
2024-03-14 | Gemserv | Part G - Pipeline Transportation Charges, Invoicing, Payment and Code Credit Rules | TBC | It was discovered that with the implementation of the Credit Control arrangements, Clause 21 in the Invoicing section was overwriiten by the new arrangements, however, there were 3 definitions that were sitting in that clause before the Mod was implemented and those 3 definitions were overwrriten and only one found it's way into the definition section and it was materially altered from what it was before. This one was reveresed through IGT173 and the other definitions will need to be put back into code through a housekeeping mod. | TBC | TBC
2024-06-19 | OVO | IGT’s New Connections Domestic Sites Only IGT Non-Domestic New Connections Ancillary Document | Amend references to PS1 and PS2 to PSA and PSB. | IGT094F intention was for all reference to PS1 and PS2 be changed to PSA and PSB, however both documents still refer to PS1 and PS2. | TBC | TBC
2024-06-15 | BUUK | Part N | Amend to reference General Terms section D | Currently referenced General Terms Section B but should be D and relates to CDSP & UK Link. | TBC | TBC
2024-06-15 | BUUK | Part E | Amend 14.1 reference to GTB2.4.1 to say GTB2.5.1. | TPD 5.13.10 reference to GTB2.4.1 is changing to GTB2.5.1. | TBC | TBC
2024-06-15 | BUUK | Part K | Amend 23.10 to change reference from V5.15 to V5.5. | Incorrect paragraph referenced | TBC | TBC

## Known Issues - Closed
Last Reviewed: 7th November 2024
Issue | Details | Date Raised | Raised By | Meeting Reference | Action Required | Last Update | Comments
iGT Meter Point Creation Process | Following discussions between iGTs and Xoserve, it has become apparent that a Shipper, other than the PSR Shipper, is able to take over ownership of a meter point without the PSR Shipper necessarily being informed. This results in the first Shipper registration on Xoserve’s system may not be the Elected Shipper. | 2016-03-01 | Paul Orlser (Xoserve) | Modification Workstream 16-03 | Guidance to be provided on this issue and the proper process to be followed in the Meter point creation process and industry flows. | 2017-08-01 | Paul Orsler (Xoserve) investigated this issue and a report will be produced for the iGTs when a solution has been finalised.
Interaction and communication with the Project Nexus Transition Progress Group (TPG) | Do issue relating to TPG groups go straight to the TPG or are they to be discussed within iGT UNC Workstreams. | 2016-04-03 | - | Modification Workstream 16-04 | Determine where TPG issues should be directed to | 2016-06-07 | This issue is being discussed in the Transition Progress Group (TPG) discussions. Updates are to be provided to the iGT UNC when available and or required.
RGMA and its medium of transmission: | Understand whether iGTs would be mandated to send RGMA flows (ONJOB/ONUPD), and by what means iGTs would be expected to send flows (i.e. IX or alternative) | 2016-04-03 | Paul Orlser (Xoserve) | Modification Workstream 16-04 | Relates to IX directories and there is an outstanding issue on how this will be performed. | 2017-08-01 | Slides have been provided to iGTs by Xoserve.
Processing for in-flight queries during the on-effective window before Project Nexus go-live | Some queries could potentially be stuck inflight following the non-effective days period and go live of SSP | 2016-04-03 | - | Modification Workstream 16-05 | Determine how in-flight queries will be managed during the non-effective days window and communicate this approach with all iGT UNC parties | 2016-06-07 | This issue is being discussed in the Transition Progress Group (TPG) discussions. Updates are to be provided to the iGT UNC when available and or required.
Transportation Set-up rates | An issue that has been identified by iGTs during Project Nexus Market Trials relating to iGT charge rate effective date data. The data validation currently exists to prevent iGT rate data from being accepted where the relevant effective date exists in the past. This validation is based on requirements captured in the Agency Services BRDs for Project Nexus (UNC mod 0440). Whilst this requirement is valid for annual inflationary uplift of iGT charges, it creates an issues for iGTs in reflecting the appropriate effective dates for those charges that are revised as a result of 'business as usual' activities. | 2016-06-08 | - | Modification Workstream 16-07 | iGTs have been advised to provide a prospective future effective date for charging rate data to be accepted in the Supply Point Register. | 2017-08-01 | The Work Group (16-07) noted this issue as Closed.
Development of iGT086 - CDSP Changes UNC Modification 0565 | The progression of iGT086 is reliant on the development of UNC 0565 Modification. If UNC 0565 is delayed, then iGT086 will also be delayed, and will not be able to meet the planned November 2016 Panel determination date. | 2016-06-07 |  | Modification Workstream 16-06 | Monitor the progress of UNC 0565 | 2017-08-01 | iGT086 developed and implemented on 1st June 2017.
Potential Modification to be raised by JR regarding triggers for transportation charges | JR believes that there is not enough in the legal text to allow iGT's the permission to trigger transportation charges. JR will be raising a modification in early 2017 after reviewing iGT080 which Mandating iGT use of Supply Meter Points registered on The Pipeline Operators’ Agent’s Supply Point Register for Shipper Transportation Billing | 2016-11-01 |  | Modification Workstream 16-11 |  | 2017-08-01 | Captured in iGT097.
Operational issues around Section D 7.4 | Section D 7.4 of iGT Code; CDSP commentary says raise a query - operationally how do we do it? Not currently covered under standard query codes as of Nexus go live. | 2017-04-04 | Kirsty Dudley (E.ON) |  |  | 2017-08-01 | BU-UK believe all meter codes were removed by the work group ahead of NEXUS and IGT100 is reinstating these. Shippers could raise a change to create a specific query code if desired but in the absence of this would expect such queries to come in via the .MFR. Shippers will however need to confirm with Xoserve the date Xoserve received the .CDN from the IGT as opposed to when the Shipper received the .CDJ or .SWN.
Change in procedure to MCS process | A change in procedure has been identified after CDSP goes live with regards to iGT Market Sector Code (MSC) validation. A step may need to be identified for iGTs to liaise with Shippers to ensure correct billing of a site (Commercial/domestic) | 2017-04-04 | Paul Orlser (Xoserve) | Modification Workstream 17-04 |  | 2017-08-01 | Xoserve validate MSC based on allowable values which are contained within files supplied by Shippers to UK Link systems. Where either 'D' or 'I' are populated within files, this is accepted and updated accordingly. iGTs are notified of changes via their daily delta file updates. iGTs have flagged concerns that Market Sector Code changes are not further validated (i.e. for legitimacy) before these take effect in central systems. Options to mitigate concerns raised by iGTs are to be developed further, with the possibility of a change being proposed in the future.
Raising certain queries for iGT MAM verification visits | iGT073 changes may leave an operational gap whereby Shippers are unable to raise queries to iGTs (as MAMs) for the investigation of certain issues (e.g. crossed meters, meter exchange query) | 2016-08-02 | Kirsty Dudley (E.ON) | Modification Workstream 16-08 | iGTs requested to respond to an email circulated on 09/09/16 | 2017-08-01 | No comments received to date on iGT073
Operational issues around Section D 7.4 | Section D 7.4 of iGT Code; CDSP commentary says raise a query - operationally how do we do it? Not currently covered under standard query codes as of Nexus go live. | 2017-04-04 | Kirsty Dudley (E.ON) | Modification Workstream 17-04 |  | 2017-08-01 | BU-UK believe all meter codes were removed by the work group ahead of NEXUS and IGT100 is reinstating these. Shippers could raise a change to create a specific query code if desired but in the absence of this would expect such queries to come in via the .MFR. Shippers will however need to confirm with Xoserve the date Xoserve received the .CDN from the IGT as opposed to when the Shipper received the .CDJ or .SWN.
House-keeping & change group issues for Guidance document iGT MAM RGMA file formats | An error has been identified in the iGT MAM RGMA File formats guidance document owned by the iGT's. This does not site in a particular code or change body. KB has to complete housekeeping on the document. | 2016-11-01 | Katy Binch (ESPUG) | Modification Workstream 16-11 | This was discussed at length & the Workgroup agreed KB to make changes and review documents. | 2018-02-06 | SPAA has now completed their review of RGMA and these changes will come into effect in June 2018. The Workgroup noted that there may have been changes made within SPAA that could effect the iGT UNC RGMA guidance document.
RGMA procedures post PNID | The new processes which are to be implemented post PNID meaning that Job transactions cannot be sent after the meter has reaches CO status. | 2016-11-01 | Paul Orlser (Xoserve) | Modification Workstream 16-11 | Discussion and presentation at the November 2016 workstream meeting. FYI | 2018-02-06 | Xoserve seeking to implement a change to the RGMA validation rules for new connections to improve the ability for Shipper to send a meter installation date prior to confirmation on UK Link systems - this is covered in UKLP262 change reference and has will be confirmed via the ChMC
Potential issues with the quality of data supplied to iGTs post Nexus | iGT097 was introduced on 1st June 2017 to enable iGTs to consecutively produce estimated invoices for transportation fees if needed after Project Nexus go live where data was missing. The old Code rules sated that iGTs would have to ask permission for this to happen and this could leave them vulnerable to cash flow issues. It still remains to be seen if these measures will need to be taken as the first round of invoicing using post Nexus data is currently underway. | 2017-08-01 | Andrew Margan (BG) | Modification Workstream 17-08 | Monitoring of this throughout the for the first few months of single service. | 2018-02-06 | This may have been superseded by iGT102 which ensures that iGTs can consecutively invoice in the event of a catastrophic system failure within the CDSP. This modification is looking at making iGT097 an enduring solution.
MSC validation for PCW access | Workgroup had concerns around Market Sector Code being used as a control to distinguish what data Price Comparison Websites (PCWs) can see in the DES system. However, as further validations are not being made on the MSC wrongly categorised meter points could be shown to PCWs which are in fact non Domestic sites. | 2017-09-05 | Victoria Parker (ESPUG) | Modification Workstream 17-09 | Workgroup to remain aware of this development. | 2018-02-06 | Rob Johnson (ESPUG) noted that he will be bringing a paper to the Workstream meeting in the new year on this issue.
ESP to updated the iGT RGMA guidance document in line with all SPAA changes before the June release date, and issue any changed document to the CA for circulation and publication. | With various changes happening around RGMA phase 2 the iGT RGMA guidance document will need to be updated in line with these changes before the June implementation date. This will then need to be submitted to the CA for circulation and discussion at a Workgroup meeting and publication on the iGT UNC website. | 2018-02-06 | Kirsty Dudley (E.ON) | Modification Workstream 18-02 | ESP to continue reviewing the changes in SPAA and aligning the document in accordance with these changes. | 2018-07-03
Inconsistent approach to including PL (planned sites) in the Portfolio Extracts by iGTs | Centrica has identified not all IGTs provide ‘planned’ status MPR portfolio data in the monthly portfolio extract. There is currently not a consistent approach across all iGTs as to whether this should be included in the extract, however, current code states 'A system generated unique identifier for the point at which a meter is, has been or will be connected to the gas network. | 2018-02-06 | Andrew Margan (BG) | Modification Workstream 18-02 | CA to send out correspondence to all iGTs to ascertain what their interpretation of code is to decide on next steps | 2018-08-07
Banding range in the CSEP NExA Table | There is a varying degree of bands in relation to the house types iGT’s receive from UIPs/Developers that do not appear in the current CSEP NExA table. This is relevant to the development of iGT071. | 2016-07-05 | Andrew Margan (BG) | Modification Workstream 16-07 | This issue is not to be included within the scope of iGT071, and a new Modification may need to be raised. | 2018-01-10 | Workgroup discussed amending 1 Bed to 1BP to align with the three character convention. The Workgroup also discussed incorporating all commonly used property types into the table to ensure that all parties are in line with Code.
Gap in the MPRN allocation process where IGTs can be allocated an MPRN range prior to having an MDD short code | Murphy Gas networks had had an MPRN range allocated to them prior to them being on the MDD and having a short code given for the UK Link system. This meant that Shippers could not update their systems and this has caused a potential issue with an IGT creating PSRs without these being able to be validated. | 2018-09-04 | Kirsty Dudley (E.ON) | Modification Workstream 18-09 | Additional steps are required to be added to the MPRN process to ensure that an IGT is on the UK Link System and has a valid MDD hat has ben registered before an MPRN range is allocated to them. |  | The Workgroup reviewed the guidance document and had one comment on adding a section on how the MRPN range is distributed to the industry. CA to make these changes.
Outcomes for UNC656 - Two alternate for Panel members - IGT currently only has provisions for one alternate. | During discussions on UNC656 the CA presented findings which highlighted that the only area for possible concern/attention was around the UNC's Panel members ability to appoint two named alternates in case they and their first named alternate as unavailable to attend a meeting. The IGT provision is for one named alternate at present. | 2018-12-04 | Chair | Modification Workstream 18-12 | The Panel to keep this on the register to monitor | 2018-12-04
Password protection protocol Ancillary Document - GDPR review | The CA highlighted that a process had fell down around the password protection protocol & that some Shippers were not changing passwords frequently enough. A review of the Ancillary Document was agreed following the implementation of GDPR. | 2018-08-07 | Kirsty Dudley (E.ON) | Modification Workstream 18-08 | E.ON providing a change marked version of the current Ancillary document of review at the next WG meeting. | 2018-03-05 | The FMR was presented to April Panel and IGT118 was put forward for implantation in the June release.
Communication between Pipeline Operators and Pipeline Users within the data sharing processes | A list of escalation contacts are held for the IGTs, however, there is not a similar list for Shippers and therefore this makes it more complex to get in touch with some shippers who are not actively engaged with the Code. | 2019-01-08 | BUUK | Modification Workstream 19-02 | Shipper list created | 2019-11-05
Issue of re-ordering of UNC (UNC708) and the consequential drafting that needs to be overlaid on the reordered IGT UNC. | RG005 and the consequential drafting for the SCRs and the impact of UNC0708. | 2020-01-09 |  | Modification Workstream 20-01 | Review of workload and development of proposals. This needs to be addressed as quickly as possible due to reduce the impact of UNC708 and to deliver the consequential drafting to Ofgem's timetable (March 2020). | 2020-07-02 | IGT137 was implemented on 24th July 2020.
The IGT MPRN Allocation Table process and the concern about running out of MPRNs. | There is no outlined processed for the replacement of MPRN when a site has completely ran out of MPRNS | 2020-04-09 | ESP | Modification Workstream 20-04 | Confirm and outline the process to IGT's | 2020-07-02 | CA confirmed the current capacity provisions of unallocated MPRNs and shared the embedded processes around industry requests and the process of requested additional allocations from Xoserve.
Increased amount of Modifications as a result COVID 19 | A possible increase of urgent modifications within the UNC as a result COVID 19 and the lack of engagement in the IGT UNC to progress them forward. | 2020-04-09 | E.ON | Modification Workstream 20-04 | Create a solution to ensure Mods raised as a result of COVID-19 are processed through IGT UNC regardless of | 2020-07-02 | IGT UNC have processed four urgent Modifications due to COVID-19. The CA does have capacity to deal with this volume of change and the process has been tested sufficiently.
SPAA MDD References | IGT124 identifies the changes required. | 2019-06-04 | Kirsty Dudley (E.ON) | Modification Workstream 19-06 | IGT124 implemented on 28th February 2020 | 2020-07-02
Asset transfer process | In the instance that the assets of one IGT has absorbed another's asset, there is no outlined process for this in terms of SLAs | 2020-04-09 | Code Administrator | Modification Workstream 20-04 | Establish and outline a process for asset transfer including SLAs. | 2020-04-09
Shipper User Verification of Supply Meter Point Isolations | The Workgroup debated around implications of pointing to the UNC when in fact the Code is incorrect where the current provision states that the Transporter is responsible for the process, where in fact this should have been changed to CDSP during the Project Nexus changes | 2019-04-02 | BUUK | Modification Workstream 19-04 | Following internal discussions in BUUK it is believed that this issue can be removed from the KIR and placed on the closed tab. Internal discussion in BUUK will continue on this, however, it is not currently relevant for the Workstream meeting. | 2020-08-13
IGT131 (Automatic updates to Meter Read Frequency) appeal | UNC629S (Automatic updates to Meter Read Frequency) has been appealed by EDF to the authority. Therefore, IGT131 is still on hold in terms of it's development in the Workgroup (the two modifications were not aligned in their development and so this is still at the development stage). | 2020-07-09 | Code Administrator | Modification Workstream 20-07 | CA to wait for the outcome of the appeal to Ofgem on UNC629S | 2020-12-03 | UNC692S is to be implemented following a rejection of the appeal by Ofgem. This modification will be withdrawn by the proposer when a date for implementation has been set by the DSC Change Management Committee as all IGT Supply Point obligations are covered in the legal text drafting of UNC692S.
Legal text drafting | There has been concerns raised over the UNC legal text drafting process and whether this takes into consideration other impacted Codes. The WG are aware that it is not the remit to draft LT for other Codes however UNC0691S has highlighted a fundamental error between the chain of IGT UNC, Proposer and Legal text provider. | 2020-07-09 | E.ON | Modification Workstream 20-07 | The Workgroup discussed this at the October Workgroup as AOB. The Code Administrator has fed into the UNC legal text drafting guidance document with suggested cross code working changes which will be discussed by the UNC panel at their November meeting. | 2020-12-03 | New guidance has been put into the UNC Panel Legal Text drafting guidance document following input from the IGT UNC Code Administrator and others. This should give sufficient steps to ensure a better cross-code working on legal text drafting.
UNC747 (Amendment of reference from AIGT to INA within the UNC) | The reference to AiGT is incorporated into IGT140 legal text which is currently with Ofgem for a deciison. If this does not get implemented the change to the references to AiGT will need to be raised as a FT Mod in the IGT UNC. | 2020-12-10 | Code Administrator | Modification Workstream 20-12 | IGT150F has been raised by BUUK following the implementation of UNC747FT. | 2021-03-04
LDZ Ancillary Agreement | Unknown agreement which sits outside of Code but has several references in Code and was found as a result of IGT148 LT. Will need to be investigated and a future decision made on whether this is still a valid agreement and is needed. | 2021-04-07 | ESPUG | Modification Workstream 21-04 | IGT to explore the origins and applicability of this agreement as soon as practicable. | 2024-02-12 | UNC TPD Section J 6.6 sets out the CSEP Ancillary Agreement (see below the extract from Code) and Section 6 sets out the provisions for Connected System Exit Points – Special Provisions, so the CSEP Ancillary Agreement is likely related to sites with large volume or unique status and would be established on site specific basis. 6.6 CSEP Ancillary Agreement 6.6.1 The Transporter may require, as a condition of a User's giving notice pursuant to paragraph 6.3.1, that the User enter into or accede to an Ancillary Agreement ("CSEP Ancillary Agreement") in a form designated by the Transporter with Condition A11(18) Approval of the Authority setting out terms (in addition to or by way of variation of the terms of the Code) in relation to the use of the relevant System for the purposes of offtake of gas at a Connected System Exit Point. 6.6.2 A CSEP Ancillary Agreement shall be deemed to be a part of the Code for the purposes of enabling such Agreement to be modified pursuant to the Modification Rules. 6.6.3 A CSEP Ancillary Agreement may contain any provision which may be included in a CSEP Network Exit Agreement, in which case any requirement that the CSEP Network Exit Agreement contain such a provision shall not apply. 6.6.4 The Transporter will make available to any User on request a copy of any CSEP Ancillary Agreement. 12/02/24 - Update from Nick King and National Gas, '“Yes, CSEP Ancillary Agreements still exist and are used for NTS CSEPs. Capacity is only referenced but only for the purposes of confirming the CSEP is a Relevant Exit point for the purposes of J6.7.1 and J6.7.2.” Nick would also would expect that DNOs also use CSEP Ancillary Agreements for non IGT CSEP e.g. Gas Act GT Licence excepted and/or exempt industrial developments.
Party Engagement Pipeline User Constituency | Issues have arisen around Pipeline User engagement in the code (linked to issue 3). Survey feedback uncovered resourcing and a lack of knowledge in the area as reasons for a lack of engagement. | 2020-07-09 | E.ON | Modification Workstream 20-07 | The Workgroup is to discuss this issue further at a future meeting, however, this will be an enduring agenda item. | 2021-05-06
Performance Assurance changes in the UNC not being picked up and replicated in the IGT UNC, therefore, leaving the codes misaligned. | There is no mandatory function in the UNC which ensures that changes made to the PA regime or it's documents (PAFD) will automatically be applied to the IGT UNC (through a Modification). This means that there is a risk of the two codes governance being misaligned whilst the regime applies to both areas. This was picked up during the IGT138 Workgroup discussions, however, it was agreed that any arrangements would need to be a post implementation change. Added to the KIR for visibility. | 2021-04-07 | E.ON | Modification Workstream 21-04 | UNC Panel Members at the June 2021 meeting voted unanimously that new issues were identified as part of consultation and that Modification 0674 should be issued to Workgroup. UNC published the amended UNC674 Modification for Workgroup discussion. The Workgroup considered the amended Modification at its meeting on 2nd February 2022 and the variation request and amended legal text on 28th February 2022. Amended UNC674 will need to be reviewed to determine the impact on IGT138. At its February meeting the UNC Panel agreed a further report extension to April 2022. The Proposer of IGT138 is reviewing the changes to 0674 with the Code Administrator with the aim of bringing the Modification to the April workgroup meeting. The Modification was considered by Workgroup and a variation request was presented to Panel at its April 2022 meeting where the Panel agreed to accept the variation and issue the Modification for consultation for 2.5 weeks. This Modification will be presented to IGT UNC Panel 24th June 2022. Both UNC0674V and IGT138V have been improved by the Authority on 29th July 2022 and are to be implemented on 1st November 2022 (Ofgem's decision) . | 2022-07-06
MAM /MEM consistency | The following defined terms are used within the IGT UNC: - Meter Asset Manager (MAM) - Meter Equipment Manager (MEM) Both terms make reference to the same role but are used interchangeably within the IGT UNC. The UNC Currently uses MAM and the REC uses MEM. BUUK have suggested that the use of terms be analysed and consideration be given to aligning with MEM (as used in the REC). | 2022-05-12 | IGT UNC Workgroup | 2022-05-22 |  | 2022-06-03
Performance Assurance Reports Register (PARR) Report was required. | Provision of data to PAC for oversight of sites paused from the Must Read process | 2022-08-04 |  |  | Consideration should be given to how this data will be provided and whether a new Performance Assurance Reports Register (PARR) Report was required. the Performance Assurance Committee (PAC) does not currently receive Must-Read process specific data. However, PAC do have the ability to see the time span between readings that have been taken (e.g. line in the sand monitoring). PAC are only monitoring whether Code requirements are being met and the length of time intervals between meter readings loading. It was agreed that a new PARR Report would be required for to specifically monitor Must-Read data and it was suggested that the data to be included could be: • the volume of IGT sites paused due to known meter issues and the length of time sites have been paused for; and • the volume of IGT sites paused due to SoLR or CoS events and the length of time sites have been paused for. The following additional points regarding this Business Rule were made: • Data for IGT UNC sites and UNC sites are combined, unless otherwise requested; • PAC does not see MRPN level data; • PAC’s powers stem from the UNC and not the IGT UNC currently; • Entities that are engaging in theft are susceptible to consistently switching, and this process could compound this risk; It was agreed that as this is new ground, the report should be delivered as part of the Modification and in Code an intent should be made where it would state that the PAC should have oversight of the process. AJ notified the Workgroup that in the past there have been issues where the report design has been stipulated in the Code and that has resulted in the report not always being fit for purpose. It was agreed that this matter would be noted in the IGT UNC Known Issues Register to be addressed at a later date. | 2024-03-14 | This Mod has been implemented and report produced to agreed to close.
CA to develop a Cross Code Ways of Working strawman. | The Panel (at its September 2022 meeting) agreed that this action (21/10 - 03) should be closed with the issue being added to the Known Issues Register in light of current priorities and Code Reform. | 2022-09-23 | Panel | 2022-09-22 | AJ to develop the Cross Code Ways of Working strawman and to bring back to Panel for review. The Panel agreed that this strawman should also include details of how Joint Workgroups would work. | 2022-10-06
Panel Shipper Representation | The IGT UNC Panel is currently facing quoracy issues in which a rationale/solution is being developed. | 2019-09-03 | E.ON | Modification Workstream 19-09 | Risk to Panel Quoracy has now been realised and the Panel is non-quorate - emergency measures have been evoked as per Code to ensure that Panel business can continue - however, this means that Shippers are very much underrepresented at Panel. IGT140, which sought to address / mitigate this issue has been rejected by the Authority and the reason will be discussed at the September Panel meeting. The IGT UNC Code Administrator received one nomination for Pipeline User representatives for the IGT UNC Panel. Claire Roberts will therefore continue on the Panel for a further two years from October 2021. Any shipper who would be interested in becoming a Panel representative should contact the Code Administrator. The Code Administrator continues to raise the quoracy issue with parties, issuing communications on a quarterly basis. Ofgem have been made aware of this issue and confirmed at the July 2023 Panel meeting that they have spoken with the relevant team in regard to this. The Code Administrator has issued another request for nominations - July 2023. The Code Administrator have received one new nomination for the IGT UNC Panel. As the current Shipper Representative is no longer continuing after their term ends in September 2023, then Shippers still only hold one representative. | 2024-03-07 | 07/03/24 - The IGT UNC now have two Shipper Panel representatives and are now quorate.

## Housekeeping - Closed
Last Reviewed: 7th November 2024
Date Raised | Raised By | Section of Code | Legal Text | Reason for change | Modification | Date Implemented
2018-12-04 | BU-UK | Part CV 2.7.1 (a)(iii) | the relevant Gas Year defined in accordance with Section H of the UNC; | The IGT UNC defines Gas Year in Part M, therefore a point across to the UNC is not needed in this instance. | IGT123 | 2019-06-28
2019-04-02 | BU-UK | Part CV 2.7.1 (a)(iii) | - | The IGT UNC defines Gas Year in Part M, therefore a point across to the UNC is not needed in this instance | IGT123 | 2019-06-28
2019-04-03 | BU-UK | Part CI 20.6 | - | The Data Protection Act of 1998 has been replaced by a new version in 2018 following GDPR developments. | IGT123 | 2019-06-28
2019-04-04 | BU-UK | Part G 20.1 | - | Reference to Microsoft Excel which could be deemed commercially bias. Amend to have referencing a generic spreadsheet format | IGT123 | 2019-06-28
2019-04-05 | BU-UK | Standards of Service Ancillary Document 3.1 (j), 5.2 and New Non-Dom & New Domestic Ancillary Documents | - | The rest of the IGT UNC uses Business Day, while these clauses references a Working Day. Correct to conform with the rest of the code. | IGT123 | 2019-06-28
2019-04-06 | BU-UK | Part CI 2.3, 5.2, Part CIV 8.1 and Part D 2.1 | - | A capitalised term has four references in code but no definition within Part M. Therefore, a similar approach is recommended for how the UNC rationalises the definition of “Isolate.” | IGT123 | 2019-06-28
2019-09-03 | BU-UK | Ancillary document password protection protocols 2.2 | and must conform to the above password configuration’ | To remove 'and must conform to the above password configuration | IGT130 | 2021-02-26
2020-02-14 | Gemserv | Removal of AIGHT and replacement with INA | - | AIGHT has recently been subsumed by INA and no longer operates under this enity.To ensure the IGT UNC is update in text | IGT150F | 2021-06-26
2021-03-04 | ESPUG | Part M | "Central Data Services Provider" or "CDSP" shall have the meaning in M1.2.1(a); | Change the M reference to N1.2.1(a) | IGT152F | 2021-06-25
2022-03-25 | IGT UNC Panel | Part G - Pipeline Transportation Charges, Invoicing, Payment and Code Credit Rules | - | To make it explicit within code text that credit cover provisions apply to transportation charges only. This housekeeping change will only be required should IGT132VV be approved. | IGT163 | 2023-06-29